## Sheet1
Product Backlog
Category | Description
User story | As a new user, I want to register and create an account for the iGym system so that I can access its features
User story | As a registered user, I want to use my login credentials created under registration to log into the iGym system
User story | As a user, I need to be able to design my own workouts from a set of predefined exercises, so that I can create structured and personalized training sessions
User story | As a user, I want to see a list of my saved workout plans upon logging in, so that I can quickly select and start my workout
User story | As a user, I want to be able to delete my old, ineffective workout plan, so that i can focus only on workout plans that will help me improve
User story | As a user, I want to be able to adjust my workout plans, so that I can continuously optimize my training, prevent plateaus, and ensure my workouts remain effective
User story | As a user, I want to log the weight and repetitions for each exercise I complete, so that I can keep track of my training progress
User story | As a user, I want to be able to learn how to correctly perform unfamiliar exercises so that I can follow my workout plan safely and effectively
Design change | The application currently lacks a UI element providing important site-wide information and navigation such as contact links, terms of service, and support resources
Design change | The current user interface lacks a component for users to efficiently access key areas of the application
User story | As a user, I want to be able to browse and select a personal trainer with expertise in a specified field, so that i can receive workout plans and guidance tailored to my individual needs
User story | As a user looking for professional guidance, I want to communicate with my personal trainer via a chat function, so that I can ask questions, receive feedback, and stay on track with my training
User story | As a user, I want to be able to receive workout plans from other users, so that I can follow a structured training routine created for me
User story | As a user, I want to be able to create a group chat so that I can communicate with multiple people at once
Development activity | The project lacks a standardized Docker environment, making it dificult to ensure consistent setup, configuration, and deployment across development and production systems
User request | As a user, I am not satisfied with the layout and organization of components on the exercise detail page and dashboard, it is both unintuitive and cluttered
Engineering improvement | The frontend codebase has become disorganized and dificult to navigate, with inconsistent structure and redundant logic, making it hard to maintain and extend
User story | As a user, I want to receive notifications for new messages so that I can stay informed about updates from my groups
User story | As a user, I want to view details about past workout sessions quickly upon login, so that I can track my progress and stay motivated
User story | As a user, I want to schedule my workout sessions in advance, so that I can effectively balance my training with other commitments
User story | As a user, I want to see an overview of my past and upcoming workouts in a calendar view, so that I can manage my training schedule effectively
User request | User and personal trainers want the ability to update their profile details
User story | As a personal trainer, I want to be able to get a calendar view of a client’s workout history and future sessions, so that I can have an overview of their consistency
User story | As a personal trainer, I want to schedule one-on-one sessions with my clients directly from a calendar view, so that I can easily organize my working schedule
User story | As a personal trainer, I want all upcoming sessions with my clients to be visible from my dashboard, so I can quickly review my work schedule
Bug | Refreshing the page causes the user profile context to be lost
Bug | Users occasionally see the same message being sent multiple times at once in chat rooms
Bug | Profile picture uploads fail silently when exceeding the unknown size limit, showing a generic and unclear error to the user
Bug | The navigation bar displays the default placeholder image instead of the user’s actual profile picture, even after it is uploaded
User request | The chat room name between me and my personal trainer is too generic, making it difficult to distinguish between chats
User request | When I am choosing a personal trainer, it only shows their usernames and specialty, making it hard to recognize or connect with the trainers
Bug | The calendar view incorrectly marks tomorrow’s date as the current day, causing confusion when tracking workout sessions
Enhancement | The dashboard intended for personal trainers is currently incomplete
Bug | When the access token expires, the system fails to utilize the refresh token to obtain a new access token, resulting in authenticated requests. Additionally, if both the access and refresh token have. Expired, the application does not properly log out the user, leading to inconsistennt session behavior