## Sheet1
SPRINT 1 BACKLOG
Category | Description | Tasks | Owner | Estimated effort | Total effort | Status
User story | As a new user, I want to register and create an account for the iGym system so that I can access its features | Frontend - Create a registration form with required fields: username, passwords, etc. | Max | 2 | 10 | Completed
|  | Backend: Design and create the necessary models and set up API endpoint to support user registration | Andreas | 2 |  | Completed
|  | Write tests to verify URL routing, model behavior, and view logic for the registration process | Karoline | 3 |  | Completed
|  | Create an acceptance test that simulates the full registration and login process | Andreas | 2 |  | Completed
|  | Write corresponding user story | Max | 1 |  | Completed
User story | As a registered user, I want to use my login credentials created under registration to log into the iGym system | Set up backend logic for login using Django REST Framework JWT | August | 3 | 7 | Completed
|  | Frontend: Create a login form and handle authentication requests to the backend | Daniel | 2 |  | Completed
|  | Write tests to verify URL routing for the login process | Max | 1 |  | Completed
|  | Write corresponding user story | Daniel | 1 |  | Completed