## Sheet1
SPRINT 2 BACKLOG
Category | Description | Tasks | Owner | Estimated effort | Total effort | Status
User story | As a user, I need to be able to design my own workouts from a set of predefined exercises, so that I can create structured and personalized training sessions | Locate a free API or a dataset that provides exercise information (e.g., image, instruction) | Max | 2 | 14 | Completed
|  | Backend: Implement database models for workouts and exercises, and set up an API endpoint for creating workouts. | Andreas | 3 |  | Completed
|  | Frontend: Develop UI that allows users to select exercises and create workout templates | Daniel | 3 |  | Completed
|  | Write view, model, and URL tests to validate workout creation | Andreas | 3 |  | Completed
|  | Implement an acceptance test that simulates a user creating a workout | Daniel | 2 |  | Completed
|  | Write corresponding user story | Max | 1 |  | Completed
User story | As a user, I want to see a list of my saved workout plans upon logging in, so that I can quickly select and start my workout | Backend: Develop an API endpoint to fetch saved workouts associated with the logged-in user | Karoline | 2 | 7 | Completed
|  | Frontend: Fetch saved workouts from the backend and implement UI to display them | Max | 2 |  | Completed
|  | Write tests to verify URL routing and view logic for displaying saved workouts | Karoline | 2 |  | Completed
|  | Write corresponding user story | Karoline | 1 |  | Completed
User story | As a user, I want to be able to delete my old, ineffective workout plan, so that i can focus only on workout plans that will help me improve | Backend: Implement API endpoint to delete a workout plan | August | 2 | 6 | Completed
|  | Frontend: Create a button on the dashboard that triggers the API call | Daniel | 1 |  | Completed
|  | Write view and URL tests to validate workout deletion | Max | 2 |  | Completed
|  | Write corresponding user story | August | 1 |  | Completed
User story | As a user, I want to be able to adjust my workout plans, so that I can continuously optimize my training, prevent plateaus, and ensure my workouts remain effective | Backend: Develop an API endpoint to handle updates to workout plans | Karoline | 2 | 10 | Completed
|  | Frontend: Implement UI that allows a user to adjust their workout plans, such as name, exercises, etc. | Max | 3 |  | Completed
|  | Write tests to validate URL and view logic for updating a workout | Daniel | 2 |  | Completed
|  | Create a feature test that simulates a user updating one of his workouts | August | 2 |  | Completed
|  | Write corresponding user story | Karoline | 1 |  | Completed
User story | As a user, I want to log the weight and repetitions for each exercise I complete, so that I can keep track of my training progress | Backend: Implement database models for workout session, and set up an API endpoint to create workout sessions | Andreas | 3 | 14 | Completed
|  | Frontend: Create UI for users to enter weight, repetitions, and sets for a workout session | Daniel | 3 |  | Completed
|  | Find a formula to calculate calories burned under a session | August | 2 |  | Completed
|  | Write tests to validate URL, model and view logic for creating a workout session | August | 3 |  | Completed
|  | Write a feature test that simulates a user performing a workout session | Daniel | 2 |  | Completed
|  | Write corresponding user story | Andreas | 1 |  | Completed
User story | As a user, I want to be able to learn how to correctly perform unfamiliar exercises so that I can follow my workout plan safely and effectively | Backend: Set up an API endpoint to serve detailed information about a specific exercise, and find a way to store and serve images | August | 2 | 10 | Completed
|  | Frontend: Build a UI component to show detailed instructions, images, and information for each exercise | Karoline | 2 |  | Completed
|  | Write tests to validate URL routing and view logic for retrieving information about an exercise | Andreas | 2 |  | Completed
|  | Write a feature test simulating a user navigating to an unfamiliar exercise | Karoline | 2 |  | Completed
|  | Add a search bar and category filter to the exercise list | Karoline | 1 |  | Completed
|  | Write corresponding user story | August | 1 |  | Completed
Design change | The application currently lacks a UI element providing important site-wide information and navigation such as contact links, terms of service, and support resources | Design and implement a footer component in the frontend that includes the neccessary site information | Daniel | 2 | 2 | Completed
Design change | The current user interface lacks a component for users to efficiently access key areas of the application | Design and implement a navigation bar that provides intuitive access to the main sections of the application | Max | 3 | 3 | Completed