## Sheet1
SPRINT 5 BACKLOG
Category | Description | Tasks | Owner | Estimated effort | Total effort | Status
Bug | Refreshing the page causes the user profile context to be lost | Fix user context persistence on refresh, ensure login state and profile data reload correctly | August | 2 | 2 | Completed
Bug | Users occasionally see the same message being sent multiple times at once in chat rooms | Prevent duplicate chat messages by ensuring each message is only sent and stored once | Daniel | 2 | 2 | Completed
Bug | Profile picture uploads fail silently when exceeding the unknown size limit, showing a generic and unclear error to the user | Enforce maximum upload size for profile images, and display a clear error message when a user selects a file that exceeds the allowed limit | Daniel | 1 | 1 | Completed
Bug | The navigation bar displays the default placeholder image instead of the user’s actual profile picture, even after it is uploaded | Ensure that the navigation bar dynamically loads and displays the authenticated user’s reaf profile picture if available | Max | 2 | 2 | Completed
User request | The chat room name between me and my personal trainer is too generic, making it difficult to distinguish between chats | Update chatroom naming convention to include both the client’s and the personal trainer’s usernames for clarity | Andreas | 1 | 1 | Completed
User request | When I am choosing a personal trainer, it only shows their usernames and specialty, making it hard to recognize or connect with the trainers | Update the UI to also show each personal trainer’s profile picture and full name | Max | 3 | 3 | Completed
Bug | The calendar view incorrectly marks tomorrow’s date as the current day, causing confusion when tracking workout sessions | Fix the date-handling logic so that the calendar accurately reflects the actual current date | Max | 1 | 1 | Completed
Enhancement | The dashboard intended for personal trainers is currently incomplete | Complete the development of the personal trainer dashboard by implementing the remaining components and functionalities | Karoline | 3 | 3 | Completed
Bug | When the access token expires, the system fails to utilize the refresh token to obtain a new access token, resulting in authenticated requests. Additionally, if both the access and refresh token have. Expired, the application does not properly log out the user, leading to inconsistennt session behavior | Fix the token management logic to ensure that a new access token is automatically requested using the refresh token when applicable, and that the user is logged out when both have expired | August | 5 | 5 | Completed
Development activity | The project lacks a standardized Docker environment, making it dificult to ensure consistent setup, configuration, and deployment across development and production systems | Set up Docker environment for the project and ensure proper configuration | August | 3 | 3 | Completed
User request | As a user, I am not satisfied with the layout and organization of components on the exercise detail page and dashboard, it is both unintuitive and cluttered | Redesign the exercise detail page and dashboard to address user feedback | Karoline | 3 | 3 | Completed