## Sheet1
SPRINT 3 BACKLOG
Category | Description | Tasks | Owner | Estimated effort | Total effort | Status
User story | As a user, I want to be able to browse and select a personal trainer with expertise in a specified field, so that i can receive workout plans and guidance tailored to my individual needs | Backend: Build endpoint to retrieve all trainer profiles | Max | 2 | 9 | Completed
|  | Frontend: Fetch trainers, and implement UI that lists the trainers with relevant data, allowing users to search by name and filter by specialization | Karoline | 2 |  | Completed
|  | Validate the backend by creating URL and view tests | Max | 2 |  | Completed
|  | Implement an acceptance test simulating a user browsing through the personal trainers and selecting the desired one | August | 2 |  | Completed
|  | Write the corresponding user story | Karoline | 1 |  | Completed
User story | As a user looking for professional guidance, I want to communicate with my personal trainer via a chat function, so that I can ask questions, receive feedback, and stay on track with my training | Backend: Set up API endpoint to assign a personal trainer to a user | Andreas | 2 | 7 | Completed
|  | Frontend: Create UI that initializes a chatroom when a user selects a personal trainer | Daniel | 2 |  | Completed
|  | Write view tests to verify the functionality of selecting a personal trainer | Andreas | 2 |  | Completed
|  | Write the corresponding user story | Karoline | 1 |  | Completed
User story | As a user, I want to be able to receive workout plans from other users, so that I can follow a structured training routine created for me | Backend: design new message model type to allow users to share workout plans with each others | August | 1 | 5 | Completed
|  | Frontend: Further extend the real-time chat UI to allow users to send their workout plans to other users | Andreas | 2 |  | Completed
|  | Write model tests to validate the new message type | Andreas | 1 |  | Completed
|  | Write the corresponding user story | Karoline | 1 |  | Completed
User story | As a user, I want to be able to create a group chat so that I can communicate with multiple people at once | Investigate how real-time group messaging using WebSockets in Django Channels work | Andreas | 3 | 19 | Completed
|  | Backend: implement WebSocket routing and group chat handling logic using Django Channels | Daniel | 5 |  | Completed
|  | Frontend: Build the chatroom UI with a sidebar for creating and selecting chatrooms, and a main area for sending and displaying messages in real time | Daniel | 5 |  | Completed
|  | Write view, model, and URL tests to validate chatroom and message creation | August | 3 |  | Completed
|  | Create a feature test simulating a user creating a chatroom with other users | Daniel | 2 |  | Completed
|  | Write corresponding user story | Karoline | 1 |  | Completed
Design change | The layout and organization of components on the exercise list page, exercise detail page and dashboard is both unintuitive and cluttered | Create UX wireframes for application layout | Karoline | 1 | 3 | Completed
|  | Frontend: Redesign exercise list page and exercise detail page | Karoline | 1
|  | Frontend: Redesign client dashboard | Karoline | 1
Team member | Effort
Max | 4
Andreas | 10
Daniel | 14
Karoline | 9
August | 6
Total effort | 43