## Sheet1
SPRINT 4 BACKLOG
Category | Description | Tasks | Owner | Estimated effort | Total effort | Status
Engineering improvement | The frontend codebase has become disorganized and dificult to navigate, with inconsistent structure and redundant logic, making it hard to maintain and extend | Refactor the frontend code to improve maintainability, performance, and readability | August | 8 | 8 | Completed
User story | As a user, I want to receive notifications for new messages so that I can stay informed about updates from my groups | Backend: Create API endpoints to create and list notifications for messages | Daniel | 3 | 10 | Completed
|  | Frontend: Implement UI to display notifications for new messages on the dashboard | Daniel | 3 |  | Completed
|  | Write view, model, and URL tests to validate creation and retrieval of message | Karoline | 3 |  | Completed
|  | Write corresponding user story | Daniel | 1 |  | Completed
User story | As a user, I want to view details about past workout sessions quickly upon login, so that I can track my progress and stay motivated | Backend: Create an API endpoint to retrieve past workout session data for the logged-in user | Andreas | 2 | 7 | Completed
|  | Frontend: Implement UI to display past workout session details on the dashboard | Karoline | 2 |  | Completed
|  | Implement unit tests to validate URL routing and view logic | Andreas | 2 |  | Completed
|  | Write the corresponding user story | Karoline | 1 |  | Completed
User story | As a user, I want to schedule my workout sessions in advance, so that I can effectively balance my training with other commitments | Backend: Develop model and set up API endpoint to create scheduled workout sessions | Max | 3 | 11 | Completed
|  | Frontend: Extend the calendar UI to allow users to schedule upcoming workout sessions | Max | 2 |  | Completed
|  | Write view, model, and URL tests to validate scheduled workout session creation | Andreas | 3 |  | Completed
|  | Write a feature test simulating a user scheduling a upcoming workout session | Karoline | 2 |  | Completed
|  | Write corresponding user story | Karoline | 1 |  | Completed
User story | As a user, I want to see an overview of my past and upcoming workouts in a calendar view, so that I can manage my training schedule effectively | Find a open-source UI template for a calendar that can be integrated to display workout sessions | August | 1 | 11 | Completed
|  | Backend: Create a API endpoint to retrieve scheduled workout sessions | Max | 2 |  | Completed
|  | Frontend: Fetch previous workout sessions and scheduled workout sessions from the backend and display them in the calendar view | Karoline | 3 |  | Completed
|  | Write tests to verify URL routing and view logic for listing scheduled workouts | Andreas | 2 |  | Completed
|  | Write a feature test that simulates a user navigating to the calendar view to find previous and upcoming workout sessions | Andreas | 2 |  | Completed
|  | Write the corresponding user story | Max | 1 |  | Completed
User request | User and personal trainers want the ability to update their profile details | Backend: create an update endpoint to handle modifications to user and trainer attributes | Max | 2 | 7 | Completed
|  | Frontend: Implement UI for users and personal trainers to view and edit their account details | Max | 3 |  | Completed
|  | Write view and URL tests to ensure user and trainer attribute updates are handled correctly | August | 2 |  | Completed
User story | As a personal trainer, I want to be able to get a calendar view of a client’s workout history and future sessions, so that I can have an overview of their consistency | Backend: develop API endpoints to retrieve a client’s session history and scheduled sessions | Andreas | 2 | 10 | Completed
|  | Frontend: Re-use the calendar UI to display a client’s past and upcoming workout sessions | Max | 3 |  | Completed
|  | Write view and URL tests to verify the backend logic for personal trainers retrieving their client’s session data | August | 2 |  | Completed
|  | Write a feature test simulating a personal trainer navigating to one of his client’s calendar to view their past and upcoming sessions | August | 2 |  | Completed
|  | Write the corresponding user story | Andreas | 1 |  | Completed
User story | As a personal trainer, I want to schedule one-on-one sessions with my clients directly from a calendar view, so that I can easily organize my working schedule | Backend: Design and create the necessary models and set up API endpoint to support creation of trainer-client sessions | Daniel | 3 | 11 | Completed
|  | Frontend: extend the calendar UI to allow personal trainers to schedule one-on-one session with clients | Max | 2 |  | Completed
|  | Write tests to verify URL routing, model behavior, and view logic for trainer-client session bookings | Daniel | 3 |  | Completed
|  | Write a feature tests simulating a personal trainer scheduling a session with one of his clients from the calendar | Andreas | 2 |  | Completed
|  | Write corresponding user story | Karoline | 1 |  | Completed
User story | As a personal trainer, I want all upcoming sessions with my clients to be visible from my dashboard, so I can quickly review my work schedule | Backend: Create API endpoint to retrieve upcoming sessions with clients for the logged-in trainer | Karoline | 2 | 7 | Completed
|  | Frontend: Fetch upcoming sessions with clients and implement UI to display them on the trainer’s dashboard | Daniel | 2 |  | Completed
|  | Write URL and view tests to verify backend logic | Andreas | 2 |  | Completed
|  | Write the corresponding user story | Karoline | 1 |  | Completed
Team member | Effort
Max | 18
Andreas | 18
Daniel | 15
Karoline | 16
August | 15
Total effort | 82